## Task_Table
ID | Active | Task Mode | Name | Duration | Start | Finish | Predecessors | Outline Level | Notes
1 | Yes | Manually Scheduled | Creacion del proyecto | 4 days | August 17, 2019 8:00 AM | August 21, 2019 5:00 PM |  | 1
2 | Yes | Manually Scheduled | Definición del proyecto | 1 day | August 17, 2019 8:00 AM | August 17, 2019 5:00 PM |  | 2
3 | Yes | Manually Scheduled | Definición de roles y responsabilidades | 3 days | August 17, 2019 5:00 PM | August 21, 2019 5:00 PM | 2 | 2
4 | Yes | Manually Scheduled | Documentación inicial | 13 days | August 22, 2019 8:00 AM | September 8, 2019 5:00 PM | 1 | 1
5 | Yes | Manually Scheduled | Estimación de tiempos requeridos por recursos | 1 day | August 22, 2019 8:00 AM | August 22, 2019 5:00 PM | 3 | 2
6 | Yes | Manually Scheduled | Definición de Sprint | 1 day | August 23, 2019 8:00 AM | August 23, 2019 5:00 PM | 5 | 2
7 | Yes | Manually Scheduled | Definición de actividades para realizar el proyecto y milestones | 2 days | August 24, 2019 8:00 AM | August 26, 2019 5:00 PM |  | 2
8 | Yes | Manually Scheduled | Analisis de riesgos del proyecto (AMEF) | 10 days | August 27, 2019 8:00 AM | September 8, 2019 5:00 PM | 7 | 2
9 | Yes | Manually Scheduled | Analisis de requerimientos para el sistema | 10 days | August 27, 2019 8:00 AM | September 7, 2019 5:00 PM | 7 | 2
10 | Yes | Manually Scheduled | Configuracion de herramientas | 5 days | August 23, 2019 8:00 AM | August 29, 2019 5:00 PM | 1 | 1
11 | Yes | Manually Scheduled | Instalacion del ambiente de desarrollo | 1 day | August 23, 2019 8:00 AM | August 23, 2019 5:00 PM |  | 2
12 | Yes | Manually Scheduled | Creacion repositorio de Git | 2 days | August 23, 2019 8:00 AM | August 26, 2019 5:00 PM |  | 2
13 | Yes | Manually Scheduled | Creacion ambiente de edicion de documentos | 3 days | August 27, 2019 8:00 AM | August 29, 2019 5:00 PM |  | 2
14 | Yes | Manually Scheduled | Inicializacion de perifericos | 10 days | August 30, 2019 8:00 AM | September 12, 2019 5:00 PM | 10 | 1
15 | Yes | Manually Scheduled | Realizar lectura de entrada analogica (ADC) | 2 days | August 30, 2019 8:00 AM | August 31, 2019 5:00 PM |  | 2
16 | Yes | Manually Scheduled | Realizar configuracion del PWM | 2 days | August 30, 2019 8:00 AM | August 31, 2019 5:00 PM |  | 2
17 | Yes | Manually Scheduled | Obtener Input Capture para el sensor de efecto Hall | 2 days | September 6, 2019 8:00 AM | September 7, 2019 5:00 PM |  | 2
18 | Yes | Manually Scheduled | Realizar configuracion del protocolo SPI para la pantalla LCD | 2 days | September 6, 2019 8:00 AM | September 7, 2019 5:00 PM |  | 2
19 | Yes | Manually Scheduled | Realizar el protocolo de comunicacion UART | 4 days | September 9, 2019 8:00 AM | September 12, 2019 5:00 PM | 18,17 | 2
20 | Yes | Manually Scheduled | Desarrollo Algoritmo de control | 10 days | September 13, 2019 8:00 AM | September 26, 2019 5:00 PM | 14 | 1
21 | Yes | Manually Scheduled | Definición del controlador a utilizar | 1 day | September 13, 2019 8:00 AM | September 13, 2019 5:00 PM |  | 2
22 | Yes | Manually Scheduled | Definición de la base del tiempo por medio de interrupciones o temporizador | 1 day | September 14, 2019 8:00 AM | September 14, 2019 5:00 PM |  | 2
23 | Yes | Manually Scheduled | Creacion del modelo de control | 4 days | September 16, 2019 8:00 AM | September 19, 2019 5:00 PM | 22,25 | 2
24 | Yes | Manually Scheduled | Realizar simulaciones del sistema | 2 days | September 20, 2019 8:00 AM | September 22, 2019 5:00 PM | 23 | 2
25 | Yes | Manually Scheduled | Realizar el calculo de la velocidad | 1 day | September 13, 2019 8:00 AM | September 13, 2019 5:00 PM |  | 2
26 | Yes | Manually Scheduled | Implementacion del algoritmo de control en C | 4 days | September 23, 2019 8:00 AM | September 26, 2019 5:00 PM | 24 | 2
27 | Yes | Manually Scheduled | Desarrollo Interfaz de usuario | 7 days | September 22, 2019 8:00 AM | September 29, 2019 5:00 PM |  | 1
28 | Yes | Manually Scheduled | Definición del formato para la informacion del usuario | 4 days | September 22, 2019 8:00 AM | September 25, 2019 5:00 PM |  | 2
29 | Yes | Manually Scheduled | Configuracion del display | 2 days | September 26, 2019 8:00 AM | September 27, 2019 5:00 PM | 28 | 2
30 | Yes | Manually Scheduled | Pruebas del funcionamiento del display viendo los datos del sistema | 2 days | September 28, 2019 8:00 AM | September 29, 2019 5:00 PM | 29 | 2
31 | Yes | Manually Scheduled | Pruebas de Verificacion | 16 days | September 30, 2019 8:00 AM | October 19, 2019 5:00 PM | 27 | 1
32 | Yes | Manually Scheduled | Evaluacion estandar de programacion | 5 days | September 30, 2019 8:00 AM | October 4, 2019 5:00 PM |  | 2
33 | Yes | Manually Scheduled | Pruebas de caja blanca | 2 days | October 4, 2019 8:00 AM | October 5, 2019 5:00 PM |  | 2
34 | Yes | Manually Scheduled | Documentación de resultados pruebas de caja blanca | 4 days | October 7, 2019 8:00 AM | October 10, 2019 5:00 PM | 33 | 2
35 | Yes | Manually Scheduled | Pruebas de caja negra | 2 days | October 4, 2019 8:00 AM | October 5, 2019 5:00 PM |  | 2
36 | Yes | Manually Scheduled | Documentación de resultados pruebas de caja negra | 2 days | October 7, 2019 8:00 AM | October 8, 2019 5:00 PM | 35 | 2
37 | Yes | Manually Scheduled | Calculo de la complejidad ciclomatica | 1 day | October 11, 2019 8:00 AM | October 11, 2019 5:00 PM |  | 2
38 | Yes | Manually Scheduled | Puebas e integracion | 6 days | October 12, 2019 8:00 AM | October 18, 2019 5:00 PM |  | 2
39 | Yes | Manually Scheduled | Mediciones de throughput, RAM y Flash | 2 days | October 18, 2019 8:00 AM | October 19, 2019 5:00 PM |  | 2
40 | Yes | Manually Scheduled | Documentación de Resultados | 47 days | August 23, 2019 8:00 AM | October 26, 2019 5:00 PM | 1 | 1
41 | Yes | Manually Scheduled | Creacion reporte final con analisis de resultados | 46 days | August 23, 2019 8:00 AM | October 25, 2019 5:00 PM |  | 2
42 | Yes | Manually Scheduled | Presentacion final | 1 day | October 26, 2019 8:00 AM | October 26, 2019 5:00 PM | 40 | 1

## Resource_Table
ID | Name | Initials | Type | Material Label | Group | Email Address | User Logon Account | Max Units | Standard Rate | Cost Per Use | Notes
1 | Product Owner | P | Work |  |  |  |  | 40% | $0.00/h | 0
2 | Scrum Master | S | Work |  |  |  |  | 100% | $0.00/h | 0
3 | Scrum Team member Engineer 1 | E1 | Work |  |  |  |  | 100% | $0.00/h | 0
4 | Scrum Team Engineer 2 | E2 | Work |  |  |  |  | 100% | $0.00/h | 0
5 | Scrum Team Engineer 3 | E3 | Work |  |  |  |  | 100% | $0.00/h | 0

## Assignment_Table
Task Name | Resource Name | % Work Complete | Work | Units
Definición del proyecto | Product Owner | 0 | 1.8h | 20%
Definición del proyecto | Scrum Master | 0 | 9h | 100%
Definición del proyecto | Scrum Team Engineer 2 | 0 | 9h | 100%
Definición del proyecto | Scrum Team Engineer 3 | 0 | 9h | 100%
Definición del proyecto | Scrum Team member Engineer 1 | 0 | 9h | 100%
Definición de roles y responsabilidades | Scrum Master | 0 | 96h | 100%
Definición de roles y responsabilidades | Scrum Team Engineer 2 | 0 | 96h | 100%
Definición de roles y responsabilidades | Scrum Team Engineer 3 | 0 | 96h | 100%
Estimación de tiempos requeridos por recursos | Scrum Master | 0 | 9h | 100%
Estimación de tiempos requeridos por recursos | Scrum Team Engineer 2 | 0 | 9h | 100%
Estimación de tiempos requeridos por recursos | Scrum Team Engineer 3 | 0 | 9h | 100%
Definición de Sprint | Scrum Master | 0 | 9h | 100%
Definición de Sprint | Scrum Team Engineer 2 | 0 | 9h | 100%
Definición de Sprint | Scrum Team Engineer 3 | 0 | 9h | 100%
Definición de actividades para realizar el proyecto y milestones | Scrum Master | 0 | 57h | 100%
Analisis de riesgos del proyecto (AMEF) | Scrum Master | 0 | 297h | 100%
Analisis de requerimientos para el sistema | Scrum Team Engineer 2 | 0 | 27.3h | 10%
Analisis de requerimientos para el sistema | Scrum Team Engineer 3 | 0 | 27.3h | 10%
Analisis de requerimientos para el sistema | Scrum Team member Engineer 1 | 0 | 27.3h | 10%
Instalacion del ambiente de desarrollo | Scrum Team Engineer 2 | 0 | 9h | 100%
Creacion repositorio de Git | Scrum Team member Engineer 1 | 0 | 16.2h | 20%
Creacion repositorio de Git | Scrum Team Engineer 3 | 0 | 16.2h | 20%
Creacion ambiente de edicion de documentos | Scrum Team Engineer 3 | 0 | 5.7h | 10%
Creacion ambiente de edicion de documentos | Scrum Team member Engineer 1 | 0 | 5.7h | 10%
Realizar lectura de entrada analogica (ADC) | Scrum Team Engineer 2 | 0 | 3.3h | 10%
Realizar lectura de entrada analogica (ADC) | Scrum Team Engineer 3 | 0 | 3.3h | 10%
Realizar lectura de entrada analogica (ADC) | Scrum Team member Engineer 1 | 0 | 3.3h | 10%
Realizar configuracion del PWM | Scrum Team Engineer 2 | 0 | 3.3h | 10%
Realizar configuracion del PWM | Scrum Team Engineer 3 | 0 | 3.3h | 10%
Realizar configuracion del PWM | Scrum Team member Engineer 1 | 0 | 3.3h | 10%
Obtener Input Capture para el sensor de efecto Hall | Scrum Team Engineer 2 | 0 | 3.3h | 10%
Obtener Input Capture para el sensor de efecto Hall | Scrum Team Engineer 3 | 0 | 3.3h | 10%
Obtener Input Capture para el sensor de efecto Hall | Scrum Team member Engineer 1 | 0 | 3.3h | 10%
Realizar configuracion del protocolo SPI para la pantalla LCD | Scrum Team Engineer 2 | 0 | 3.3h | 10%
Realizar configuracion del protocolo SPI para la pantalla LCD | Scrum Team Engineer 3 | 0 | 3.3h | 10%
Realizar configuracion del protocolo SPI para la pantalla LCD | Scrum Team member Engineer 1 | 0 | 3.3h | 10%
Realizar el protocolo de comunicacion UART | Scrum Team Engineer 2 | 0 | 16.2h | 20%
Realizar el protocolo de comunicacion UART | Scrum Team Engineer 3 | 0 | 8.1h | 10%
Realizar el protocolo de comunicacion UART | Scrum Team member Engineer 1 | 0 | 8.1h | 10%
Definición del controlador a utilizar | Scrum Team Engineer 2 | 0 | 0.9h | 10%
Definición del controlador a utilizar | Scrum Team Engineer 3 | 0 | 0.9h | 10%
Definición del controlador a utilizar | Scrum Team member Engineer 1 | 0 | 0.9h | 10%
Definición de la base del tiempo por medio de interrupciones o temporizador | Scrum Team Engineer 2 | 0 | 0.9h | 10%
Definición de la base del tiempo por medio de interrupciones o temporizador | Scrum Team Engineer 3 | 0 | 0.9h | 10%
Definición de la base del tiempo por medio de interrupciones o temporizador | Scrum Team member Engineer 1 | 0 | 0.9h | 10%
Creacion del modelo de control | Scrum Team Engineer 2 | 0 | 76.95h | 95%
Realizar simulaciones del sistema | Scrum Team Engineer 2 | 0 | 5.7h | 10%
Realizar simulaciones del sistema | Scrum Team Engineer 3 | 0 | 5.7h | 10%
Realizar simulaciones del sistema | Scrum Team member Engineer 1 | 0 | 5.7h | 10%
Realizar el calculo de la velocidad | Scrum Team Engineer 2 | 0 | 0.9h | 10%
Realizar el calculo de la velocidad | Scrum Team Engineer 3 | 0 | 0.9h | 10%
Realizar el calculo de la velocidad | Scrum Team member Engineer 1 | 0 | 0.9h | 10%
Implementacion del algoritmo de control en C | Scrum Team Engineer 2 | 0 | 64.8h | 80%
Definición del formato para la informacion del usuario | Scrum Team Engineer 2 | 0 | 8.1h | 10%
Definición del formato para la informacion del usuario | Scrum Team Engineer 3 | 0 | 8.1h | 10%
Definición del formato para la informacion del usuario | Scrum Team member Engineer 1 | 0 | 8.1h | 10%
Configuracion del display | Scrum Team Engineer 3 | 0 | 3.3h | 10%
Configuracion del display | Scrum Team member Engineer 1 | 0 | 3.3h | 10%
Pruebas del funcionamiento del display viendo los datos del sistema | Scrum Team Engineer 2 | 0 | 3.3h | 10%
Pruebas del funcionamiento del display viendo los datos del sistema | Scrum Team Engineer 3 | 0 | 3.3h | 10%
Pruebas del funcionamiento del display viendo los datos del sistema | Scrum Team member Engineer 1 | 0 | 3.3h | 10%
Evaluacion estandar de programacion | Scrum Team Engineer 3 | 0 | 10.5h | 10%
Evaluacion estandar de programacion | Scrum Team member Engineer 1 | 0 | 10.5h | 10%
Pruebas de caja blanca | Scrum Team Engineer 2 | 0 | 3.3h | 10%
Pruebas de caja blanca | Scrum Team Engineer 3 | 0 | 3.3h | 10%
Pruebas de caja blanca | Scrum Team member Engineer 1 | 0 | 3.3h | 10%
Documentación de resultados pruebas de caja blanca | Scrum Team member Engineer 1 | 0 | 8.1h | 10%
Pruebas de caja negra | Scrum Team Engineer 2 | 0 | 3.3h | 10%
Pruebas de caja negra | Scrum Team Engineer 3 | 0 | 3.3h | 10%
Pruebas de caja negra | Scrum Team member Engineer 1 | 0 | 3.3h | 10%
Documentación de resultados pruebas de caja negra | Scrum Team member Engineer 1 | 0 | 3.3h | 10%
Calculo de la complejidad ciclomatica | Scrum Team Engineer 2 | 0 | 0.9h | 10%
Calculo de la complejidad ciclomatica | Scrum Team Engineer 3 | 0 | 0.9h | 10%
Calculo de la complejidad ciclomatica | Scrum Team member Engineer 1 | 0 | 0.9h | 10%
Puebas e integracion | Scrum Team Engineer 2 | 0 | 15.3h | 10%
Puebas e integracion | Scrum Team Engineer 3 | 0 | 15.3h | 10%
Mediciones de throughput, RAM y Flash | Scrum Team Engineer 2 | 0 | 3.3h | 10%
Mediciones de throughput, RAM y Flash | Scrum Team Engineer 3 | 0 | 3.3h | 10%
Mediciones de throughput, RAM y Flash | Scrum Team member Engineer 1 | 0 | 3.3h | 10%
Creacion reporte final con analisis de resultados | Scrum Team Engineer 2 | 0 | 76.05h | 5%
Creacion reporte final con analisis de resultados | Scrum Team Engineer 3 | 0 | 76.05h | 5%
Creacion reporte final con analisis de resultados | Scrum Team member Engineer 1 | 0 | 76.05h | 5%